## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
|  | 1 | Foundations required for doing project | MUST HAVE | No Dependencies | Atmakuri Bhuvanesh | 3- Completed
|  | 2 | LLM for Contract analysis | MUST HAVE | No Dependencies | Atmakuri Bhuvanesh | 3- Completed
|  | 3 | Clause Identification and Risk Analysis Engine | MUST HAVE | No Dependencies | Atmakuri Bhuvanesh | 3- Completed
|  | 4 | Update tracking and Contract Modification | MUST HAVE | No Dependencies | Atmakuri Bhuvanesh | 3- Completed
Note on F1: ====== ID#AAABv6zxcdw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | DDd
[8 empty] | 0 | 46381 | 0 | 0 | 0 | 46386 | 46387 | 46023 | 46024 | 46025 | 46026 | 46027 | 46028 | 46029 | 46030
SPRINT 1 BACKLOG
1 |  | Foundations required for doing project | Nov 10th | Nov 24th |  |  |  |  | Nov 10th | Nov 11th | Nov 12th | Nov 13th | Nov 14th | Nov 15th | Nov 16th | Nov 17th | Nov 18th | Nov 19th | Nov 20th | Nov 21th | Nov 22nd | Nov 23rd
1 |  | Foundations required for doing project | Nov 10th | Nov 24th | Atmakuri Bhuvanesh | Learnt and Practiced all the fundamentals required for the project | Done |  | Introduction Session | Python and Jupyter Installation | Python Keywords and Naming Conventions | Python Variables | Python Data Types | Revised variables, Named Keywords | Revised Sets, Dictionaries, List, and Tuples | Range(), Mutable, Immutable, and Flow Controls | Flow control and Functions | Python Functions and their types | Python Modules | Python OOPS | Constructors, and Instance Variables | Revised Constructors
In
2 |  | LLM for Contract Analysis | Nov 25th | Dec 29th | Column1 | Column2 |  |  | Nov 24th | Nov 25th | Nov 26th | Nov 27th | Nov 28th | Nov 29th | Nov 30th | Dec 1st | Dec 2nd | Dec 3rd | Dec 4th | Dec 5th | Dec 6th | Dec 7th
2 |  | LLM for Contract Analysis | Nov 25th | Dec 9th | Atmakuri Bhuvanesh | Understood about the project, LLM and Executed Demo codes | Done |  | Project Understanding | Presentation about project | Creation of Virtual Environment | Introduction of Tech tools | Project Presentation Session | Revised Python Concepts | Practiced Python Concepts | Prompt Engineering | Data Science,AI,GenAI,LLM | LLM and Creation of Groq API key | Groq API implementation | Package and Workflow for Milestone 2 | Revised Prompt Engineering | Revised Packages
3 |  | Clause Identification and Risk Analysis Engine | Dec 10th | Dec 24th |  |  |  |  | 8th Dec | 9th Dec | 10th Dec | 11th Dec | 12th Dec | 13th Dec | 14th Dec | 15th Dec | 16th Dec | 17th Dec | 18th Dec | 19th Dec | 20th Dec | 21st Dec
3 |  | Clause Identification and Risk Analysis Engine | Dec 10th | Dec 24th | Atmakuri Bhuvanesh | Understood Clause Extraction and Risk Analysis Engine | Done |  | Workflow and Project Structure | Workflow and Text Extraction from pdf | Text Extraction and Overlapping | Clause Identification and Chunking | Clause Extraction | Revision on Clause Extraction | Revision on Chunking | Discussed about the assignment | Risk Analysis Engine | run & Pipeline Code and Intro on Regulatory Update Tracking | Practiced milestones 1 and 2 | Regulatory update Tracking | Worked on Assignment 1 | Worked on Assignment 1
4 |  | Regulatory Update Tracking System & Contract Modification | Dec 25th | Jan 8th |  |  |  |  | 2026-12-25 | Dec 27rth | Dec 28th | Dec 29th | 2026-12-30 | 2026-12-31 | 2026-01-01 | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08
4 |  | Regulatory Update Tracking System & Contract Modification | Dec 25nd | Jan 8th | Atmakuri Bhuvanesh | Understood Regulatory Update Tracking System & Contract Modification | Done |  | Worked on Assignment | Assignment Presentation | Regulatory Update Tracking System | Regulatory Update Tracking System and Assignment Presentation | Executed Demo 2 & 3 codes and Bulding the Regulatory Update Tracking | Discussed the progress | Practiced Demo codes | Contract Modification and Ammendment Engine | Revised Milestone 2 | Implementation of Milestone 3 | Revised Milestone 3 Codes | FeedParser and Milestone 3 execution | Slack Integration | Practised Milestone3
Note on D2: ====== ID#AAABv5noruQ Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABv6zxceE Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABv6zxceM Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABv6zxceY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABv6zxceU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABv6zxceA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABv5noruA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABv5noruI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABv6zxcec Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABv6zxceI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABv6zxcd4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABv6zxcd8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABv5noruM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABv5noruU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABv6zxceQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABv5noruE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABv6zxcd0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7